## Sheet1
Glossary
Visitor: A person who enters to site
User: Visitor who signed up and logged in
Glossary: List of Topics
Topic: Consists of topic title, topic description, topic content and label(s)
Topic Content: Contains topic image(s) and topic text
Topic Statistic: Consist of enrolled user number, accuracy of the quiz answers
Learning Path: A consecutive collection of topic content and related quiz
Quiz: A collection of questions
Question: Related with specific Content and created by users as a step of a Learning-Path for others to explore
User Profile: Consists of user email, created topic list, enrolled topic list, enrolled topic statistics
Activity: Action of a user defined by the W3C in https://www.w3.org/TR/activitystreams-core/
Activity Stream: Collection of activities defıned ın JSON-LD format
Annotation: A piece of comment in JSON-LD format created by a User on a page in the system related to an image or a text
Annotation-Server: A stand-alone, separate server that contains and serves all annotations
Label: Wiki tag related to content which is created by the owner of the content
Requirements | Status | Comments
1. Non-functional Requirements
1.1. Back-end shall use the following database system: PostgreSQL | Done | -
1.2. Back-end shall be written in Java | Done | -
1.3 Developed application should be deployed to web | Done | -
1.4 System language shall be English | Done | -
1.5 System shall have continuous integration / continuous development implementation through CircleCI | Done | -
1.6 Static Code analysis shall be done through Sonar Cloud | Done | -
1.7 As an acceptance criteria there should be 80 percent of code coverage on Back-end codes | Done | -
1.8 System development shall be followed via Github | Done | -
1.9. All Annotations should be stored in a stand-alone Annotation-Server | Done | -
1.10. All Annotations should be retrieved from a stand-alone Annotation-Server | Done | -
2. Functional Requirements
2.1. Visitor Requirements
2.1.1 Visitor shall be able to see the landing, glossary, signup and login pages. | Done | -
2.1.2 Visitor and user shall be able to search glossary. | Future Work Required | Feature has to be improved. Search is only filtering topic titles at the moment.
2.1.3 Visitor shall be able to sign up as a user. | Future Work Required | Login request requires constrain validation exception.
2.1.4 Email and Password shall be required for sign up. | Done | -
2.1.5 Email shall be unique. | Done | -
2.1.6 Email and password shall be required for log in. | Done | -
2.2. Topic Requirements
2.2.1 User shall be able to create topic. | Done | -
2.2.2 Topic shall have a title. | Done | -
2.2.3 Topic shall have at least one tag. | Done | -
2.2.4 Topic shall have a description. | Done | -
2.2.5 Topic shall be seen by users. | Done | -
2.2.6 Topics shall be listed in glossary. | Done | -
2.2.7 Topic shall have more than one learning path. | Done | -
2.2.8 Topic shall have zero or many quiz. | Done | -
2.2.9 Topic statistic shall be seen by topic owner. | Canceled | This was the requirement from the last semester.
2.3. API Requirements
2.3.1 User shall be able to search api with keyword(s). | Future Work Required | Feature has to be improved. Search is only filtering topic titles at the moment.
2.3.2 User shall be able to select zero or many result from api search. | Done | -
2.3.3 User shall use selected api result(s) in his/her topic. | Done | -
2.4. Quiz Requirements
2.4.1 Learning path shall have at least one quiz. | Done | -
2.4.2 A quiz shall have at least one question. | Done | -
2.4.3 Question shall be related with content. | Done | -
2.4.4 Question shall have five options with only one correct answer. | Done | There is no option number restriction at the moment.
2.5 User Requirement
2.5.1 User shall be able to update the owned topic. | Done | -
2.5.2 User shall be able to update the learning path which belongs to owned topic. | Done | -
2.5.3 User shall be able to update the quiz which belongs to owned topic. | Done | -
2.5.4 User shall be able to see quiz when the quiz is started. | Done | -
2.5.5 User shall be able to continue the learning path after answering the all questions correctly. | Canceled | This was the requirement from the last semester.
2.5.6 User shall be able to restart the quiz. | Canceled | This was the requirement from the last semester.
2.5.7 User shall see his/her own user profile. | Done | -
2.5.8 User statistics shall be stored with enrolled topic(s) and quiz answers. | Canceled | This was the requirement from the last semester.
2.5.9 User statistics shall be displayed in user profile. | Canceled | This was the requirement from the last semester.
2.5.10 Users should be able to follow another Users | Done | -
2.5.11 Users should be able to follow Labels | Done | -
2.6 Activity Requirements
2.6.1 Users should be able to see the Activities of the Users which they are following | Done | -
2.6.2 Activity Streams should be generated by the system. | Done | -
2.7 Annotation Requirements
2.7.1 Users should be able to create an Annotation for an image on a page | Done | -
2.7.2 Users should be able to create an Annotation for a selected text on a page | Done | -
2.7.3 Users should be able to see all the Annotations created on a page in the platform | Done | -
2.8 Recommendation System
2.8.1 Users should be able to see Recommendations based on the Labels and Users that they are following | Failed | Requires the understading of sparql. Wikidata api does not have proper features to search related wikis.

## Sheet2
Total | 49
Done | 40
Future Work Needed | 3
Failed | 1
Canceled | 5
Total | 44
Done | 40
Future Work Needed | 3
Failed | 1
Total Requirements: 49